## ComponentInventory
Stream | Screen/View Name | UI Component name | MCR | Sprint | Status | Sub Status (Completed) | Source Component Name | Dependent Component Avaibility | Sources Component Issues | Dependent Service Name | Dependent Service Availability | ScreenShot | Comments
COB | Estate Data Entry Form | EstateSetup | 6 | Sprint 17 | Dev Complete | UI Dev - Mock Data | wf-calendar-picker | Yes |  | No | No | EstateSetup
COB | Estate Data Entry Form | BasicInfoContainer | 6 | Sprint 17 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, wf-dropdown | Yes | Yes | No | No | BasicInfoContainer
COB | Estate Data Entry Form | TaxAffiliationContainer | 6 | Sprint 17 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, wf-dropdown, wf-radio, wf-select, wf-checkbox | Yes |  | No | No | TaxAffiliationContainer
COB | Estate Data Entry Form | LargeTrader | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-calendar-picker | Yes |  | No | No | LargeTrader
COB | Estate Data Entry Form | InstitutionalConsulting | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, | Yes |  | No | No | InstitutionalConsulting
COB | Estate Data Entry Form | EDelivery | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-button, wf-checkbox, wf-radio, wf-tooltip | Yes |  | No | No | EDelivery
COB | Estate Data Entry Form | EmailContainer | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, wf-select, wf-checkbox, wf-tooltip, | Yes |  | No | No | EmailContainer
COB | Estate Data Entry Form | Scap | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-radio, | Yes |  | No | No | Scap
COB | Estate Data Entry Form | InvestmentExperience | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-input, wf-select, wf-checkbox, | Yes |  | No | No | InvestmentExperience
COB | Estate Data Entry Form | PartyAddressComponent | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, wf-dropdown, wf-select, wf-checkbox | Yes |  | No | No | PartyAddressComponent
COB | Estate Data Entry Form | AlternateNamesComponent | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, wf-select | Yes |  | No | No | AlternateNamesComponent
COB | Estate Data Entry Form | TelphonesContainer | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, wf-dropdown, wf-select, wf-checkbox, wf-drawer, wf-table, wf-tooltip, wf-reorder | Yes |  | No | No | TelphonesContainer
COB | Estate Data Entry Form | FinancialContainer | 6 | Sprint 17 | Dev Complete | UI Dev - Mock Data | wf-button, wf-input, wf-dropdown, wf-select, wf-checkbox, wf-tooltip | Yes |  | No | No | FinancialContainer
COB | Estate Data Entry Form | InvestmentInterest | 6 | Sprint 17 | Dev Complete | UI Dev - Mock Data | wf-multiselect-dropdown | Yes |  | No | No | InvestmentInterest
ALL | All | PageHeader | 6 | Sprint 16 | Dev Complete | UI Dev - Mock Data | Typography | Yes |  | No | No
ALL | PrepAccount | PrepAccount | 7 | Sprint 18 | Dev In Progress | UI Dev - Mock Data | wf-button, wf-input, wf-dropdown, wf-select, wf-multiselect-dropdown | Yes |  | No | No | PrepAccount
ALL | PrepAccount | RMA Domestic | 7 | Sprint 18 | Dev In Progress | UI Dev - Mock Data | wf-dropdown, wf-multiselect-dropdown | Yes |  |  |  | RMA Domestic
ALL | PrepAccount | RMA International | 7 | Sprint 18 | Dev In Progress | UI Dev - Mock Data | wf-dropdown, wf-multiselect-dropdown | Yes |  |  |  | RMA International
COB | PrepAccount | Account-Party Search | 7 | Sprint 18 | Not Started | UI Dev - Mock Data | wf-button, wf-input, wf-dropdown, | Yes |  | SearchPartyService | Yes
COB | PrepAccount | Account-Party Search result | 7 | Sprint 18 | Not Started |  | wf-table | Yes |  | RelatedParties | Yes
ALL | All | Left navigation |  |  |  |  | Left Navigation | No |  |  |  | Left navigation
ALL | All | DMS Document Upload |  |  | Not Started |  | Upload component | No |  |  |  | DMS Document Upload
ALL | All | Horizontal progress bar |  |  | Not Started |  | Horizant Progress Bar | No |  |  |  | Horizontal progress bar
AM | Account Maintenance | Tiles View |  |  | Not Started |  | Tiles View | No
ALL | ALL | Bread Crumb |  |  | Not Started |  | wf-action-menu | Yes
ALL | All | TableContainer |  |  | Not Started |  | wf-table | Yes |  |  |  | TableContainer
ALL | Multiple | GridContainer |  |  | Not Started |  | wf-table | Yes |  |  |  | GridContainer
AM | Single Registration Title Container | RegistrationTitleContainer | 6 | Sprint 17 | Dev Complete |  | wf-drawer, wf-input, wf-button, wf-tooltip | Yes | Yes | Stage/account/registration-title | Yes | RegistrationTitleContainer
AM | Client Profile Details | ClientProfileDetailsContianer | 6 | Sprint 17 | Dev Complete |  | wf-input, wf-dropdown, wf-select, wf-checkbox, wf-radio | Yes | Yes | Stage/account-change/party-name/ | Yes | ClientProfileDetailsContianer
AM | Account Ownership Changes Landing Page | AccountOwnershipDetailsContainer | 6 | Sprint 17 | Dev Complete |  | wf-dropdown, wf-select | Yes | Yes | Stage/account-change/new-registration-title | Yes | AccountOwnershipDetailsContainer
AM | Account Ownership Changes Landing Page | AuthorizationContainer | 6 | Sprint 17 | UI Dev |  | wf-calendar-picker, wf-input, wf-radio, wf-button | Yes | Yes | Stage/account-change/name-change | Yes | AuthorizationContainer
AM | Account Ownership Changes Landing Page | PartyInformation | 6 | Sprint 17 | Dev Complete |  | wf-table, wf-input | Yes | Yes | Stage/account/parties | Yes | PartyInformation
AM | Account Ownership Changes Landing Page | RegistrationTitleContainer | 6 | Sprint 17 | Dev Complete |  | wf-tooltip, wf-input | Yes | Yes | Stage/account/parties | Yes | RegistrationTitleContainer
AM | Account Ownership Changes Landing Page | SuitabilityProfile | 6 | Sprint 17 | UI Dev |  | wf-tooltip, wf-radio, wf-select, wf-checkbox | Yes | Yes | Stage/account/parties | Yes | SuitabilityProfile
AM | Account Ownership Changes Landing Page | AccountClassification | 6 | Sprint 17 | UI Dev |  | wf-button, wf-icon | Yes | Yes | Stage/account/parties | Yes | AccountClassification
AM | Review Multiple Registration Accounts | ReviewAccountDetailsContainer | 7 | Sprint 18 | Dev Complete |  | wf-icon, wf-tooltip, wf-checkbox | Yes | Yes | Stage/account/parties | Yes | ReviewAccountDetailsContainer
AM | Review Multiple Registration Accounts | Sole Owner | 7 | Sprint 18 | Dev Complete |  | wf-table, wf-checkbox, wf-tooltip | Yes | Yes | registration-title | Yes
AM | Conolidated Address View | AddressDetailsContainer | 7 | Sprint 18 | Dev Complete |  | wf-card, wf-label, AddressTileLayoutContainer | Yes | No | Stage/account/account-and-required-party-profile | Yes | ViewConsolidatedAddressesContainer
Note on F1: Deevi, Pavan Kumar x19567: - available (per schedule) - awaiting ( from FA/other sources)

## Defination
Status | Sub Status
Not Started | Not Started
Blocked | Grooming
Dev In Progress | Design
Dev Complete | UI Dev - Static Data
UI Dev - Mock Service
UI Dev - API Integration
Demo

## ScreenShots-COB
Search
TaxAffiliationContainer
PrepAccount
Left navigation
DMS Document Upload
Horizontal progress bar
TableContainer
GridContainer
Setup Information
Bussiness Information
Large Trader
Institutional Consulting
eDelivery
Email
SCAP
Investment Experience
Party Address
Alternet Names
Telephone
Financial
Investment Interest

## ScreenShots-AM
Search
ClientProfileDetailsContianer
AccountOwnershipDetailsContainer
AuthorizationContainer
PartyInformation
RegistrationTitleContainer
SuitabilityProfile
AccountClassification
ReviewAccountDetailsContainer
Sole Owner
ConsolidatedAddressesViewContainer